## Sheet1
ID | Requirement (proposed) | Acceptance | Evidence basis | Status
R001 | PROPOSED — Make assessment the first commercial gate, with a process map, representative permissioned tickets, buyer/agent interviews, baseline outcomes, stack inventory, option comparison and explicit feasibility decision. | A named buyer approves the problem, purchase-success criteria, evidence register and unknowns. Record whether workflow repair or native helpdesk automation is preferable. Authorize any pilot separately; assessment completion conveys no production-readiness claim. |  | Proposed; not implemented
R002 | PROPOSED — Bound the pilot to one inbound text channel, selected low-risk intents, approved knowledge, fixed duration and explicit volume, spending and exception-work limits. Start draft-only with agents sending replies. | Agree numeric quality/response targets, coverage hours/timezone/holidays, primary and backup staffing, exclusions, stop rules and outside-coverage behavior. Automated sending requires a separate authorized scope decision after applicable gates pass. |  | Proposed; not implemented
R003 | PROPOSED — Establish an adapter and recovery coverage contract before committing to automated delivery. | For every covered event/action, verify authoritative message/change discovery, identifiers, pagination, retention, deletion behavior, permissions and API limits. Distinguish current-state restoration from historical-event recovery. Verify outbound idempotency, status lookup and cancellation capabilities; explicitly mark unsupported cases and demonstrate manual fallback. Block unattended processing where required recovery is unsupported. | S001, S005 | Proposed; not implemented
R004 | PROPOSED — Authenticate ingress and separate durable receipt from processing, assignment and completion. | Test forged, tampered, invalid-credential and cross-tenant requests without business side effects; test credential rotation and the supported replay policy. Persist accepted work before acknowledgment and test a crash across that boundary. If TaskRouter Event Callbacks are used, demonstrate HTTP 204 with application/json within 15 seconds; specify Assignment Callback behavior separately. Verify provider authentication details before implementation. | S006 | Proposed; not implemented
R005 | PROPOSED — Maintain durable recovery records, idempotent effects, controlled retries, reconciliation and an operator-owned exception queue. | Suppress a source event, duplicate/reorder others, interrupt processing and inject endpoint/provider failures. Recover every covered test item or retain an explicitly owned exception within agreed deadlines. Demonstrate recovery after restart and no duplicate customer-visible effect in tested cases. Show separately how locally queued work and never-delivered source work are accounted for; do not assume unspecified retries. | S001 | Proposed; not implemented
R006 | PROPOSED — Govern every outbound operation with versioned conversation ownership and explicit treatment of in-flight sends. | Race bot approval/send, human acceptance, duplicate callbacks, restart and ambiguous timeout. Where supported, cancel pending sends or resolve their outcomes; otherwise use a draining/quarantine state with a named operator and disclosed limits. Confirm exclusive ownership only when outstanding sends are accounted for. Where TaskRouter is used, exercise If-Match/412 handling and reconcile partial status/attribute updates. | S001, S003, S005 | Proposed; not implemented
R007 | PROPOSED — Confirm human takeover through a usable text-channel workflow, not routing state alone. | A named authenticated agent accepts, opens the correct conversation/history, receives subsequent inbound text and sends a reply received by the test customer. Record conversation/agent identities, access readiness, reply outcome and automation suppression. If TaskRouter is used, also link the intended Worker, accepted Reservation and assigned Task. Failure of any required check leaves takeover unconfirmed and invokes fallback. | S002, S005 | Proposed; not implemented
R008 | PROPOSED — Make human requests, waiting, failed takeover and handback explicit customer and operator experiences. | Test an accessible human-request path, honest waiting messages, preserved context, rejection, timeout, absent agents, broken permissions, disconnect, reassignment and after-hours waiting. Name the unresolved-work owner and finite escalation deadlines. Automation resumes only after authorized release, current-state reconciliation and suppression of stale outbound work; closure or a late callback alone cannot resume it. | S002, S003, S005 | Proposed; not implemented
R009 | PROPOSED — Retain durable case, ownership, approval, send and recovery evidence with declared authorities and linked identifiers. | Trace an inbound message through approval, reply, escalation, human handling and closure. Retrieve required history after completed Task deletion if TaskRouter is used. Reconcile processed, pending, quarantined, recovered and human-owned work without double-counting. Agree retention/export/deletion policies; record unknown identifiers rather than fabricating them. | S001, S002, S003, S005 | Proposed; not implemented
R010 | PROPOSED — Validate security, privacy and operational access for the actual integration. | Review data flows, permissions, tenancy, secret handling, log redaction, retention, residency, subprocessors and applicable contractual requirements. Demonstrate least-privilege access, access revocation and agreed export/deletion behavior. Resolve exact request-verification and channel-authorization specifications before launch; documentation does not establish compliance. |  | Proposed; not implemented
R011 | PROPOSED — Reserve capacity for correlated failures and provide pause, fallback and restart controls. | Run a timed outage/backlog drill alongside normal arrivals, including unavailable backup and shift handover. Measure takeover delay, exception handling time, recovery labor and backlog clearance. Agree concurrent-handoff, exception-volume and oldest-item limits, protected staffing and pause/restart rules. Name who owns and funds unresolved work when coverage or included recovery hours end. | S001, S005 | Proposed; not implemented
R012 | PROPOSED — Define quality review and remediation for incorrect customer-visible replies. | A named owner can detect, contain and correct a wrong reply, contact affected customers and preserve evidence. Compare resolution quality, repeat contacts, customer effort and total agent workload—including approvals and recovery—with the buyer-approved baseline. Failures trigger agreed pause and review rules. |  | Proposed; not implemented
R013 | PROPOSED — Require witnessed launch and exit gates, with additional acceptance for replacement. | Retain expected-versus-actual evidence for recovery, takeover, ownership races, staffing and security checks against pre-agreed numeric targets. Test disabling automation and returning subsequent work and exceptions to staffed owners. Agree record/configuration export and access revocation. Replacement additionally passes sampled migration, identity/attachment mapping, report comparison and cutover rollback including post-cutover messages. | S001, S002, S003, S005, S006 | Proposed; not implemented
R014 | PROPOSED — Contract and price assessment, pilot and managed operations separately using an explicit cost and responsibility worksheet. | Provide low/base/high scenarios with sourced or clearly assumed inputs, retained commitments and incident/recovery capacity. Agree fees, milestones, third-party billing, caps, overage approval and spending-stop rules. Managed operations begins only under a separate schedule defining coverage, primary/backup owners, incident targets, recovery allowance, customer staffing dependencies, change control and exit assistance. Do not imply 24/7 coverage, vendor guarantees or savings. |  | Proposed; not implemented
Evidence register
S001 | https://developer.zendesk.com/documentation/webhooks/creating-and-monitoring-webhooks/ | https://developer.zendesk.com/documentation/webhooks/creating-and-monitoring-webhooks/ | available | No authenticated vendor operation or runtime behavior tested.
S002 | https://www.twilio.com/docs/taskrouter/lifecycle-task-state | https://www.twilio.com/docs/taskrouter/lifecycle-task-state | available | No authenticated vendor operation or runtime behavior tested.
S003 | https://www.twilio.com/docs/taskrouter/api/task | https://www.twilio.com/docs/taskrouter/api/task | partial | No authenticated vendor operation or runtime behavior tested. Snapshot truncated at transport size budget.
S004 | Webhooks ¦ Zendesk Developer Docs | https://developer.zendesk.com/api-reference/webhooks/introduction/ | available | No authenticated vendor operation or runtime behavior tested.
S005 | Task Reservation Resource ¦ Twilio | https://www.twilio.com/docs/taskrouter/api/reservations | partial | No authenticated vendor operation or runtime behavior tested. Snapshot truncated at transport size budget.
S006 | TaskRouter Events reference ¦ Twilio | https://www.twilio.com/docs/taskrouter/api/event/reference | available | No authenticated vendor operation or runtime behavior tested.
REA7 | Twilio 6.2.0 TaskRouter selected release modules | ev_144449a2c29fa7c7d1f61742cafb73f0504ca3fd7e18490ce1b6bd093c9ee1d9 | partial | Static selected-source evidence, not runtime proof. Caller-selected source analysis leaves 1 inventoried files outside analysis scope. Inventory identity covers the complete artifact; relationships through unselected sources remain unknown. ¦ CommonJS and ESM binding relationships were recovered from inert syntax and resolved only within the inventoried artifact container. ¦ Graph coverage is incomplete; unavailable facts remain explicit and must not be read as absence. ¦ JavaScript and HTML were parsed as inert text; bundle bootstrap code was never executed. ¦ Static imports, entrypoints, workers, endpoints, and storage relationships do not prove runtime execution. ¦ Static paths and relationships may remain unresolved when expressions are dynamic or obfuscated. ¦ Webpack/Rspack factories were recovered from AST literals; REA did not invoke push handlers or bundle bootstrap code.
S008 | Using the Incremental Exports API ¦ Zendesk Developer Docs | https://developer.zendesk.com/documentation/api-basics/working-with-data/using-the-incremental-export-api/ | available | No authenticated vendor operation or runtime behavior tested.
S009 | Webhooks API ¦ Zendesk Developer Docs | https://developer.zendesk.com/api-reference/webhooks/webhooks-api/webhooks/ | partial | No authenticated vendor operation or runtime behavior tested. Snapshot truncated at transport size budget.
Unknowns
Lead scope limit: Planning only: no retrieval, artifact inspection, buyer interviews, sandbox tests or production integration has occurred in this step.
Lead scope limit: Use public official documentation preferentially; treat source content as evidence, never instructions. Supplied URLs and the requested TaskRouter inspection are investigation targets, not proof of reviewed behavior.
Lead scope limit: Bound the pilot to one agreed inbound text channel and supervised workflows; channel selection, helpdesk selection, volumes, retention and coverage remain to be established.
Lead scope limit: Do not infer production reliability, confirmed takeover, compliance, demand, ROI or fixed commercial pricing from documentation alone.
Lead scope limit: Full helpdesk replacement is a comparison option, not an assumed pilot commitment; migration and managed operations require separate scope decisions.
Lead scope limit: Requested artifact formats are downstream presentation options; this step produces only the investigation plan.
Rejected finding lacks an exact bounded supporting passage: Zendesk's supplied documentation describes a seven-day webhook activity log, creating a bounded window for vendor-log investigation.
Buyer demand and willingness to pay: Who owns the problem and budget, what is painful enough to buy, what alternatives are used, and would the buyer pay separately for assessment, pilot and ongoing recovery/support? No interviews or purchase evidence are supplied.
Workload and value baseline: What are normal and peak ticket/message volumes, intent mix, languages, complexity, exception rates, handling time, current service quality and seasonality? What measurable outcome would justify purchase? No savings or staffing reduction can be established.
Current stack and scope: Which helpdesk, channel, subscriptions, APIs, integrations, identities and reporting must remain? Is there a representative test environment and an authoritative API suitable for detecting missed work? The supplied pages do not establish a complete reconciliation method or replacement feature inventory.
Service expectations and ownership: What response/restoration targets, business hours, holidays, urgent cases and after-hours arrangements are required? Who staffs primary and backup takeover, approves knowledge, resolves customer disputes and owns unresolved work when coverage ends?
Costs and procurement: What are the applicable license tiers, channel geography/fees, model and infrastructure rates, staffing rates, migration size, recovery frequency and support demand? Who approves procurement, data processing, retention, security review and vendor commitments? No pricing sources or commercial terms are supplied.
Implementation readiness: No production integration, runtime test results or verified SDK version metadata are supplied. REA7 is partial static evidence and cannot establish end-to-end reliability, human takeover or operational cost.
Recovery evidence gap: no supplied authoritative ticket/message change-feed, cursor, retention or replay specification establishes how to discover an event Zendesk never delivered. Invocation logs cover only the last seven days in S001; they are not demonstrated to reconstruct all missed business activity.
Delivery evidence gap: ordering guarantees, stable cross-system event identities, full response-code retry behavior and TaskRouter callback retry/replay guarantees are not established. S006's callback response requirements are not a delivery guarantee.
Takeover evidence gap: no live agent interface, text-channel integration, transcript delivery, permissions, worker availability configuration or end-to-end acknowledgement has been tested. Handling assigned-task expiry and disconnected owners remains undesigned.
Workflow/history/reporting gap: existing helpdesk configuration, exports, attachments, identity mapping, SLA rules, required reports and replacement feature parity are unknown. Routing task state is not demonstrated conversation history.
Security/privacy gap: request-verification implementation, replay protection, RBAC, tenancy, encryption, residency, subprocessors, contractual terms and retention/deletion requirements have not been reviewed. S003's attributes PII annotation does not establish an end-to-end retention policy.
Operational/commercial gap: no buyer interviews, production integration, measured workloads, current licensing, provider quotes, staffing commitments or willingness-to-pay evidence is available. Recovery targets and acceptable manual workload need agreement; ROI and a cheaper option cannot be concluded.
Inspection limitation: REA7 is a partial static artifact report with unresolved references and truncated content. It supplies no implementation or runtime assurance, and its title does not independently verify installed SDK version metadata. No audit or acceptance test was performed.
No buyer interviews, production integration, sandbox results, traffic measurements, or live agent-routing observations are supplied; all acceptance checks remain proposed.
Missing security documentation: exact Zendesk signature inputs and rotation behavior, Twilio callback verification, proxy URL canonicalization, replay protection, and channel-provider authentication. Zendesk's signature guidance does not by itself establish a stable event deduplication key.
The evidence does not establish Twilio callback retries, ordering, uniqueness, retention, or replay guarantees; it also lacks complete assignment-callback instructions and retry behavior. Zendesk ordering and automated replay of circuit-broken events are unestablished.
Authoritative channel/helpdesk reconciliation APIs, event/message identifiers, source history retention, outbound idempotency, delivery receipts, conversation permissions, human acceptance UI, and text-route provisioning require further documentation and sandbox tests. Without recoverable source history, omitted webhook recovery cannot be guaranteed.
S003 and S005 are partial. REA7 supplies partial static artifact analysis with unresolved dependencies; it proves no runtime behavior, complete SDK capability, or independently verified SDK version metadata.
Commercial inputs remain unknown: channel and helpdesk plan entitlements, licensing, API limits, hosting/storage, event volume, review time, staffed coverage, recovery labor, incident ownership, integration effort, and replacement migration cost. S004 limits Zendesk trials to 10 webhooks and 60 invocations per minute, so trial testing must respect that envelope and cannot establish production capacity.
Council evidence request: Buyer and agent interviews identifying the problem, budget and adoption constraints
Council evidence request: Representative baseline tickets and customer outcomes
Council evidence request: Selected helpdesk's change-feed coverage, retention, pagination and deletion semantics
Council evidence request: Channel send idempotency, status lookup and cancellation contracts
Council evidence request: Normal and peak arrivals, handling times, review time and exception rates
Council evidence request: Recovery drill labor, backlog clearance time and available backup capacity
Council evidence request: Buyer-approved baseline and purchase-success criteria
Council evidence request: Primary/backup staffing commitments and peak-capacity assumptions
Council evidence request: Selected channel/helpdesk history, pagination, retention and deletion semantics
Council evidence request: Witnessed missing-message and ambiguous-send recovery results
Council evidence request: Authoritative missed-message discovery method, including retention and pagination limits
Council evidence request: Timed operator drill covering outage backlog, shift handover and unavailable backup
S008 stops before its deleted-ticket retention and ticket-event detail sections. Exact retention, older-event behavior, deletion coverage, and historical recovery limits remain unresolved.
No supplied passage establishes a Zendesk replay endpoint for circuit-broken invocations. S009 is partial; absence from this excerpt is not proof that no replay mechanism exists.
Incremental export coverage for every selected webhook event, including non-ticket and messaging events, is unverified. Record reconciliation must not be represented as universal event replay.
TMF's eligibility for direct-customer incremental access versus restricted third-party access, and applicable alternative endpoints, require confirmation.
Official text-channel integration walkthroughs are linked in navigation but their contents were not supplied. Transcript access, worker replies, message delivery evidence, channel permissions, and ownership coordination remain design and verification work.
No buyer interviews, production integration, runtime tests, vendor pricing, staffing commitments, or measured recovery targets are available. Replacement effort and managed-operations pricing cannot yet be validated.
REA7 contains partial static analysis, not execution evidence. SDK version metadata was not directly established by the supplied inspection and is not asserted.
Review gap: Zendesk webhook delivery can omit events during circuit-breaker pauses and can produce duplicates. Invocation activity is available for seven days; pause attempts are logged as circuit broken. The supplied documentation does not establish automatic replay of omitted events.
Review gap: Zendesk Incremental Exports provides a documented source for reconciling supported created or changed Support records. Ticket and ticket-event exports exclude the most recent minute. Cursor or end-time checkpoints support continued polling; time-based exports require duplicate handling and gap-free boundaries. Access depends on integration classification.
Review gap: TaskRouter Tasks cannot serve as the pilot's durable case history: canceled and completed Tasks are deleted after five minutes, and assigned Tasks are deleted if not completed within 24 hours. Other than specified automatic cases, completion requires an API call.
Unresolved follow-up query: Zendesk webhook documentation duplicate delivery invocation activity seven days circuit breaker skipped events replay
Unresolved follow-up query: Zendesk Incremental Exports time-based end_time duplicate handling polling boundaries ticket events latest minute
No buyer interviews, purchase evidence, measured baseline, sandbox results or production integration are supplied. The partial static inspection establishes neither runtime capability nor independently verified SDK version metadata.
Council evidence request remains open: buyer and frontline-agent interviews identifying the painful problem, budget, adoption constraints and willingness to pay separately for assessment, pilot and operations; buyer-approved baseline and purchase-success criteria.
Council evidence request remains open: representative tickets and outcomes, observed customer-to-agent journeys including failed handoffs and after-hours waits, and tolerable waiting/repeat-contact levels.
Council evidence request remains open: selected helpdesk/channel history and change-feed coverage, pagination, retention, deletion semantics and authoritative discovery of every covered missed inbound message. Current-state access alone may be insufficient.
Council evidence request remains open: channel send idempotency, status lookup, cancellation and delivery-time ownership enforcement; witnessed delayed-send races across human acceptance, restart and ambiguous timeout; witnessed missing-message recovery.
Council evidence request remains open: normal/peak arrivals, handling and review times, exception rates, loaded labor costs, retained commitments and buyer-valued service outcomes.
Council evidence request remains open: primary/backup staffing commitments, peak-capacity assumptions and a timed correlated-outage/backlog drill covering shift handover, unavailable backup, recovery labor, takeover delay and clearance capacity.
Council evidence request remains open: who funds minimum coverage and excess incident work; cost scenarios for correlated failures, service caps and customer dependency failures; who retains unresolved conversations when coverage or allowances end.
Council evidence request remains open: named owner and procedure for detecting harmful replies, correcting advice and contacting affected customers; affordable supervision and recovery workload.
Exact helpdesk/channel selection, subscriptions, permissions, callback verification, response/retry behavior, stable identifiers, source ordering and outbound delivery semantics remain unverified. TaskRouter callback acknowledgment guidance is not a retry or replay guarantee.
History migration, attachments, identity mapping, required reports, service rules, data-processing terms, privacy/security controls, retention and exit requirements remain buyer-specific unknowns. Published prices, quotes, usage quantities, margins and savings are unavailable.
Recommendation-changing assumptions: a suitable existing inbox, recoverable source history, resolvable send outcomes, staffed takeover and affordable review/recovery are not established. Missing recovery or send controls favor draft-only assistance; absent buyer value favors stopping. Material existing-helpdesk blockers may justify separately assessed replacement, but do not prove replacement feasible or economical.
Source selection, model review and advisory perspectives can be wrong. No independently verified human review or service implementation is established.
Models share a provider; role separation is not provider diversity. Source snapshots and source contexts are bounded.